## Sign-off Tracker
Role | Name | Department | Sign-off Status | Date | Conditions / Notes
VP Engineering | Raj Malhotra | Engineering | Approved | 2026-08-20 | Infrastructure looks acceptable, accepting P99 risk given test env scale.
Chief Information Security Officer | Priya Deshpande | Security | Conditional | 2026-08-21 | Sign-off conditioned strictly on fixing VULN-0019 (PII export audit trail) before closing date.
VP Product | James Chen | Product | Approved | 2026-08-19 | Feature set is ready.
Director of M&A Integration | Sarah Chen | Operations | Approved | 2026-08-18 | Integration pilots completed successfully.
Chief Legal Officer | Dr. Lisa Pham | Legal | Pending | — | Blocked. Waiting on updated GDPR risk assessment from compliance team after the recent audit findings.
VP Customer Success | Tom Nguyen | Support | Approved | 2026-08-22 | Support documentation is ready.
Director of Cloud Ops | Miguel Santos | Infrastructure | Approved | 2026-08-21
Head of QA | Anita Flores | Quality Assurance | Conditional | 2026-08-22 | Sign-off conditioned on resolving the UI layout issues (VULN-0049) within first 30 days.
Chief Financial Officer | David Zhang | Finance | Approved | 2026-08-15 | Financial modeling for post-close operational expenditures looks solid.
VP Sales | Rachel Kim | Sales | Approved | 2026-08-16 | Go-to-market strategy aligned with product features.
Director of HR | Marcus Johnson | Human Resources | Approved | 2026-08-17 | Employee retention plans finalized for the acquired team.
VP Marketing | Elena Rostova | Marketing | Approved | 2026-08-18 | PR announcement draft reviewed and approved.
Chief Privacy Officer | Kevin Park | Compliance | Pending | — | Waiting to sync with Legal on the GDPR audit implications.
Director of IT | Samuel Wright | IT Support | Approved | 2026-08-19 | Hardware provisioning plan for new employees is complete.
VP Business Development | Laura Martinez | Business Dev | Approved | 2026-08-14 | Partner ecosystem transition is on track.
Chief Revenue Officer | Michael Scott | Sales | Approved | 2026-08-15 | Revenue targets for Q4 merged successfully.
Director of Design | Amanda Lee | UX/UI | Approved | 2026-08-20 | Brand guidelines sent over for app reskinning.
Head of Data Science | Vikram Patel | Analytics | Approved | 2026-08-21 | Data warehouse migration strategy is approved.