## Open Vulnerabilities
Vulnerability ID | Title | Module | Auditor Severity | Target IT Severity | Status | Assignee | Found Date | Target Fix Date | GDPR Impact | Notes
VULN-0003 | Intermittent failure in payment gateway callback | Payment Verification | Major | Major | Reopened | Kevin Park | 2026-08-04 | 2026-09-01 | No | Originally fixed in v4.1 patch 3 — now recurred. Root cause may be different
VULN-0004 | Customer search returns stale cache results after record update | Customer Search | Major | Major | In Progress | Kevin Park | 2026-08-04 | 2026-08-29 | No | only happens when Elasticsearch index refresh interval >5s
VULN-0005 | Contract conflict detection misses overlapping multi-vendor slots | Contract Scheduling | Major | Major | In Progress | Anita Flores | 2026-08-05 | 2026-09-02 | No | workaround: manually check calendar before booking
VULN-0006 | Report generation fails silently for datasets >50k rows | Report Generation | Major | Major | Under Review | Kevin Park | 2026-08-05 | 2026-09-03 | No | workaround documented in KB-4421
VULN-0007 | Notification service drops messages during Redis failover | Notification Service | Major | Major | In Progress | Kevin Park | 2026-08-05 | 2026-08-30 | No | Raj looked at this — might be a connection pool config issue
VULN-0008 | SSO token refresh race condition on concurrent browser tabs | User Auth | Minor | Minor | In Progress | Kevin Park | 2026-08-06 | 2026-08-28 | No | linked to PILOT-001 failures
VULN-0009 | SAML assertion parsing fails with special chars in display name | User Auth | Minor | Minor | Under Review | Kevin Park | 2026-08-06 | 2026-08-29 | No | edge case — only affects names with accented characters
VULN-0010 | Dashboard widget drag-and-drop broken on Firefox 115+ | Executive Dashboard | Minor | Minor | Open | Anita Flores | 2026-08-06 | 2026-09-05 | No | Firefox-specific CSS issue, Chrome/Edge fine
VULN-0011 | Bulk import CSV parser chokes on UTF-8 BOM marker | Bulk Data Import | Minor | Minor | In Progress | Kevin Park | 2026-08-06 | 2026-08-27 | No | quick fix — just strip BOM before parsing
VULN-0012 | PII export fails silently when session token expires mid-transfer | PII Data Export | Critical | Major | In Progress | Kevin Park | 2026-08-06 | 2026-09-01 | Yes | Auditor: data loss risk. Target IT: edge case, token refresh handles it in most scenarios
VULN-0013 | Calendar timezone offset wrong for offices in Arizona (no DST) | Contract Scheduling | Minor | Minor | Open | Anita Flores | 2026-08-07 | 2026-09-08 | No | Arizona doesn't observe DST — our TZ library assumes it does
VULN-0014 | Report PDF export truncates long table headers | Report Generation | Cosmetic | Cosmetic | Open | Anita Flores | 2026-08-07 | 2026-09-12 | No | cosmetic only — data is intact, just header text gets cut off
VULN-0015 | Customer record lock not released after browser crash | Customer Record | Major | Major | In Progress | Kevin Park | 2026-08-07 | 2026-08-29 | No | blocking some PILOT-002 tests. Lock expires after 30min but that's too long
VULN-0016 | API rate limiter counts OPTIONS preflight requests | API Gateway | Minor | Minor | Open | Kevin Park | 2026-08-08 | 2026-09-05 | No | CORS preflight shouldn't count against rate limit
VULN-0017 | Vendor catalog cache not invalidated on update | Vendor Catalog | Minor | Minor | In Progress | Anita Flores | 2026-08-08 | 2026-09-01 | No | stale catalog data shown until next cache refresh (15min)
VULN-0018 | Mobile layout breaks on Galaxy S21 in landscape | UI — Mobile | Cosmetic | Cosmetic | Open | Anita Flores | 2026-08-08 | 2026-09-15 | No | specific to One UI 6 browser — low priority
VULN-0019 | PII data export audit trail missing user-action-level detail | PII Data Export | Critical | Critical | In Progress | Miguel Santos | 2026-08-08 | 2026-09-02 | Yes | CISO sign-off conditioned on this fix. Linked to GDPR control AC-7
VULN-0020 | Dashboard performance widget shows wrong baseline after reset | Executive Dashboard | Minor | Minor | Waiting on Info | Anita Flores | 2026-08-09 | 2026-09-04 | No | need clarification from James on expected baseline behavior
VULN-0021 | Payment batch verification timeout not configurable | Payment Verification | Minor | Minor | Open | Kevin Park | 2026-08-09 | 2026-09-10 | No | hardcoded 30s timeout — some banks take longer
VULN-0022 | Report scheduler sends duplicate emails on DST transition | Report Generation | Minor | Minor | Open | Kevin Park | 2026-08-10 | 2026-09-12 | No | only happens twice a year, low priority
VULN-0023 | Audit trail gaps during concurrent PII access by multiple reps | Audit Trail | Critical | Major | In Progress | Miguel Santos | 2026-08-10 | 2026-09-04 | Yes | Auditor: GDPR audit trail completeness requirement. Target IT: only under >50 concurrent sessions, unlikely in prod
VULN-0024 | Customer search autocomplete flickers on slow connections | Customer Search | Cosmetic | Cosmetic | Open | Anita Flores | 2026-08-11 | 2026-09-15 | No | debounce interval too short — easy CSS/JS fix
VULN-0025 | Notification preferences UI doesn't save on first click | Notification Service | Minor | Minor | In Progress | Anita Flores | 2026-08-11 | 2026-08-29 | No | Anita says this is a CSS specificity issue, quick fix
VULN-0026 | API docs Swagger UI missing new v4.2 endpoints | API Gateway | Minor | Minor | Under Review | Kevin Park | 2026-08-11 | 2026-08-28 | No | swagger spec file needs regeneration
VULN-0027 | Meeting reminder SMS sends at UTC instead of local time | Contract Scheduling | Minor | Minor | In Progress | Kevin Park | 2026-08-12 | 2026-09-01 | No | clients getting 3am reminders — not great
VULN-0028 | Encryption at rest not applied to 3 new v4.2 data fields | Data Encryption | Major | Major | In Progress | Miguel Santos | 2026-08-12 | 2026-08-30 | Yes | new fields added in v4.2 migration missed in encryption config
VULN-0029 | Dashboard chart tooltip shows raw timestamp instead of formatted date | Executive Dashboard | Cosmetic | Cosmetic | Open | Anita Flores | 2026-08-13 | 2026-09-10 | No | cosmetic only — label wraps on screens <1280px
VULN-0030 | Bulk import progress bar stuck at 99% for large files | Bulk Data Import | Cosmetic | Cosmetic | Open | Anita Flores | 2026-08-13 | 2026-09-12 | No | import completes fine, just the progress indicator is wrong
VULN-0031 | Auto session timeout not enforced on new executive dashboard | Session Management | Blocker | Blocker | Open | Anita Flores | 2026-08-12 | 2026-09-06 | Yes | GDPR Art 32. Causes GDPR control SC-10 to be Not Met
VULN-0032 | Profile photo upload fails for HEIC format from iPhones | Customer Record | Minor | Minor | Open | Anita Flores | 2026-08-13 | 2026-09-08 | No | workaround: convert to JPEG before upload
VULN-0033 | Report builder custom date range picker resets on tab switch | Report Generation | Minor | Minor | Waiting on Info | Anita Flores | 2026-08-14 | 2026-09-05 | No | can't reproduce consistently — happens maybe 1 in 200 times
VULN-0034 | API Gateway returns 500 instead of 429 when rate limit exceeded | API Gateway | Minor | Minor | Under Review | Kevin Park | 2026-08-14 | 2026-09-03 | No | wrong HTTP status code — functional impact is the same
VULN-0035 | Vendor contract conflict alert dismisses too easily | Vendor Catalog | Major | Major | In Progress | Anita Flores | 2026-08-14 | 2026-09-01 | No | single click dismiss without confirmation — compliance risk raised by Legal
VULN-0036 | Dashboard widget config not preserved across sessions for new users | Executive Dashboard | Minor | Minor | In Progress | Anita Flores | 2026-08-15 | 2026-08-30 | No | localStorage key collision with legacy dashboard
VULN-0037 | Executive dashboard timeout causes unsaved notes to be lost | Executive Dashboard | Critical | Major | Open | Anita Flores | 2026-08-15 | 2026-09-10 | No | Auditor: data loss. Target IT: autosave covers most cases. Note: listed as 'known issue' in PR draft
VULN-0038 | Mobile navbar hamburger menu overlaps notification badge | UI — Mobile | Cosmetic | Cosmetic | Open | Anita Flores | 2026-08-16 | 2026-09-15 | No | low priority — only affects IE11 which we're dropping in v4.3
VULN-0039 | Payment verification response caching returns stale eligibility | Payment Verification | Major | Major | Under Review | Kevin Park | 2026-08-16 | 2026-09-03 | No | cache TTL should be 0 for eligibility checks — currently 5min
VULN-0040 | Customer search highlighting breaks with regex special chars in query | Customer Search | Minor | Minor | In Progress | Kevin Park | 2026-08-17 | 2026-08-30 | No | need to escape regex chars in search highlight logic
VULN-0041 | Race condition in concurrent contract write causes duplicate entries | Contract Scheduling | Critical | Critical | In Progress | Kevin Park | 2026-08-18 | 2026-08-30 | No | compliance risk — duplicate contracts possible. Fix in code review
VULN-0042 | Notification email footer shows old company address | Notification Service | Cosmetic | Cosmetic | Waiting on Info | Anita Flores | 2026-08-18 | 2026-09-10 | No | waiting on marketing for updated address block
VULN-0043 | Report export CSV uses semicolons instead of commas for EU locale | Report Generation | Minor | Minor | Open | Kevin Park | 2026-08-19 | 2026-09-10 | No | locale-aware CSV should default to commas per US standard
VULN-0044 | Memory leak during bulk PII export under sustained load | Bulk PII Export | Major | Major | In Progress | Kevin Park | 2026-08-19 | 2026-09-05 | No | Linked to perf benchmark memory threshold breach. Only occurs >2hr continuous export
VULN-0045 | Dashboard accessibility: color contrast ratio fails WCAG AA for status badges | Executive Dashboard | Minor | Minor | Under Review | Anita Flores | 2026-08-20 | 2026-09-08 | No | contrast ratio 3.8:1 — needs 4.5:1 minimum
VULN-0046 | API Gateway health check endpoint returns 200 during graceful shutdown | API Gateway | Minor | Minor | Under Review | Kevin Park | 2026-08-20 | 2026-09-04 | No | causes LB to route traffic to draining instances briefly
VULN-0047 | Profile photo thumbnail generation fails for transparent PNGs | Customer Record | Cosmetic | Cosmetic | Waiting on Info | Kevin Park | 2026-08-21 | 2026-09-12 | No | alpha channel handling issue — waiting on Chen's architecture review before fixing
VULN-0048 | Meeting reminder includes cancelled meetings in digest | Contract Scheduling | Minor | Minor | Reopened | Kevin Park | 2026-08-21 | 2026-09-05 | No | thought this was fixed in v4.1.3 — different code path
VULN-0049 | Login page background image doesn't load on first visit (cache miss) | UI — Desktop | Cosmetic | Cosmetic | Open | Anita Flores | 2026-08-22 | 2026-09-15 | No | cosmetic — white flash before image loads, only on cold cache